## Cover
PC26 — Obj 1.1D — Shah Field De-Bottlenecking Opportunities
Quantified opportunity catalogue — surface & subsurface
Issued 23-Apr-2026 · TotalEnergies ALSG × ADNOC Onshore
WORKBOOK CONTENTS
Cover | This sheet
Exec_Summary | Headline numbers + ranking + recommended sequencing
Field_Baseline | Allowable / TR / Actual breakdown — with chart
Bottleneck_Map | 9 root-cause categories (S1-S5, C1-C3, W1-W4) traced from RM comments
Opportunities_Summary | All 8 opportunities side-by-side with gain ranges + chart
Gain_Bridge | Waterfall from current 75,733 BOPD to 2026-realistic envelope
Capex_vs_Gain | Bubble/scatter view — prioritization matrix
Opp_4.1 → Opp_4.8 | One sheet per opportunity with full narrative, mechanism, prereq, gain table
Data_Gaps | Ranked list of data still required for final quantification
Field_Totals | Field-level Allowable/TR/Actual numbers from Q2-2026 Allowable file
Workshop_Agenda | Q3-2026 Technical WS agenda per KoM
FIELD-LEVEL HEADLINE
Current actual production | 75,733 BOPD
Field Technical Rate (active) | 79,983 BOPD
Gap vs TR | 4,250 BOPD (5.6 %)
Total deliverability ceiling | ~102,752 BOPD (incl. inactive)
2026 realistic uplift envelope | ~10,000–12,000 BOPD (+13 %)
Full potential envelope | ~22,000–27,000 BOPD
Number of de-bottlenecking opps. | 8 (5 subsurface + 2 surface + 1 cross-cut)
Critical missing data items | 9 (FCT report + IPM model top of list)

## Exec_Summary
Executive Summary — Top 8 De-Bottlenecking Opportunities
RANKED BY 2026-REALISTIC GAIN (BOPD)
Rank | ID | Opportunity | Category | 2026 low | 2026 high | Full low | Full high | Confidence
1 | 4.5 | WI capacity uplift (SY-175 + SY-180 + cluster review) | Subsurface / WI | 2500 | 4000 | 4000 | 5500 | Med-High
2 | 4.1 | Stimulation roll-out beyond Obj 1.1C | Subsurface | 2500 | 2500 | 5000 | 6000 | Medium
3 | 4.6 | Produced-water redistribution + R1↔R2 rebalancing | Subsurface / WI | 2000 | 2400 | 2400 | 3200 | Medium
4 | 4.7 | Surface back-pressure optimization | Surface | 1500 | 2500 | 2300 | 3300 | Medium
5 | 4.3 | VSD / PWS retrofit campaign | Surface / Completion | 1600 | 1600 | 3300 | 5500 | High
6 | 4.8 | Inactive-string reactivation acceleration | Cross-cut Obj 1.1B | 1000 | 1000 | 3920 | 3920 | High
7 | 4.2 | BHFP rate-cap relaxation via skin reduction / PVT relocalization | Subsurface | 900 | 900 | 1800 | 1800 | Med-High
8 | 4.4 | ESP upsize where pump at max frequency | Completion | 800 | 800 | 2800 | 2800 | Medium
TOTAL realistic envelope (with 25 % overlap deduction)

## Field_Baseline
Field-Level Baseline — Q2-2026 Allowable file
OIL PRODUCTION (BOPD)
Metric | Active | Including Inactive | Comment
Allowable | 76671 | 80591 | RM-approved cap
Technical Rate (TR) | 79983 | 79983 | Engineering deliverability
FAR (actual) | 75733 |  | Field actual rate Q1-2026
Gap vs TR | 4250 |  | Under-delivery 5.6 %
Deliverability ceiling |  | 102752 | Sum of estimated max for all R1+R2 strings
Inactive strings (booked) | 3920 |  | 14 strings — gain via Obj 1.1B/§4.8
WATER INJECTION (bwpd)
Scenario | Cluster #1 | Cluster #2 | Total target | Actual
With SY-175 + SY-180 commissioned | 26000 | 24600 | 50600
Without SY-175/180 (current) | 26000 | 19000 | 45000 | 53000
Technical rate | 42200 | 28800 | 71000
Cluster physical capacity (hard cap) | 26000 | 25000 | — | —

## _chart_data (hidden)
Metric | BOPD | Category | BOPD lost | Opportunity | Low | Range
Actual | 75733 | S1 — Low PIP / low intake — stim ca | 12000 | 4.5 WI capacity uplift (SY-175 + SY-180 | 2500 | 1500
Allowable | 76671 | S2 — High watercut (>60 %) — water | 7000 | 4.7 Surface back-pressure optimization | 1500 | 1000
TR | 79983 | S3 — Low BHFP — close to Pb violati | 1800 | 4.6 Produced-water redistribution + R1↔ | 2000 | 400
Allow w/ inactive | 80591 | S4 — Inactive strings — workover ba | 3920 | 4.1 Stimulation roll-out beyond Obj 1.1 | 2500 | 0
Deliverability ceiling | 102752 | S5 — Reservoir pressure depletion | 5000 | 4.3 VSD / PWS retrofit campaign | 1600 | 0
|  | C1 — Low DP across choke — VSD requ | 6500 | 4.4 ESP upsize where pump at max freque | 800 | 0
|  | C2 — ESP at max frequency | 3500 | 4.2 BHFP rate-cap relaxation via skin r | 900 | 0
|  |  |  | 4.8 Inactive-string reactivation accele | 1000 | 0
Scenario | BOPD
2026 low | 2500
2026 high | 4000
Full low | 4000
Full high | 5500
Scenario | BOPD
2026 low | 1500
2026 high | 2500
Full low | 2300
Full high | 3300
Scenario | BOPD
2026 low | 2000
2026 high | 2400
Full low | 2400
Full high | 3200
Scenario | BOPD
2026 low | 2500
2026 high | 2500
Full low | 5000
Full high | 6000
Scenario | BOPD
2026 low | 1600
2026 high | 1600
Full low | 3300
Full high | 5500
Scenario | BOPD
2026 low | 800
2026 high | 800
Full low | 2800
Full high | 2800
Scenario | BOPD
2026 low | 900
2026 high | 900
Full low | 1800
Full high | 1800
Scenario | BOPD
2026 low | 1000
2026 high | 1000
Full low | 3920
Full high | 3920

## Bottleneck_Map
Bottleneck Categories — 9 root causes from RM comments
ROOT-CAUSE CLASSIFICATION
ID | Category | Indicator phrases | Wells affected | BOPD lost vs cap | Linked opportunity | Type
S1 | Low PIP / low intake — stim candidates | "Low intake", "Low PIP", "stim required" | 32 | 12000 | §4.1 | Subsurface
S2 | High watercut (>60 %) — water management | "High water cut", "wc increase", WC>60 % | 38 | 7000 | §4.6 + Obj 1.2A | Subsurface
S3 | Low BHFP — close to Pb violation | "Limit production to get pwf above Pb", BHFP<500 psi | 12 | 1800 | §4.2 | Subsurface
S4 | Inactive strings — workover backlog | Inactive Y / Disconnected | 14 | 3920 | §4.8 + Obj 1.1B | Subsurface
S5 | Reservoir pressure depletion | Pres declining; SY-024: "improve sector VRR" | 8 | 5000 | §4.5 | Subsurface
C1 | Low DP across choke — VSD required | "Low DP across choke", "VSD required", choke fully open | 22 | 6500 | §4.3 | Surface/Completion
C2 | ESP at max frequency | "ESP running at max frequency", "freq 60 Hz" | 14 | 3500 | §4.4 | Completion
C3 | High back-pressure on flowline / station | Wells with WHFT high & low Qo at full choke | TBD | TBD | §4.7 | Surface
W1 | Cluster capacity ceiling 26 Mbwpd | "respecting max cluster capacity (25/26 Mbwpd each)" | TBD | TBD | §4.5 Phase 2 | Water Injection
W2 | WI well integrity (SY-175, SY-180) | "WO for integrity & accessibility correction" | 2 | TBD | §4.5 Phase 1 | Water Injection
W3 | R1↔R2 inter-reservoir water loss | "Water loss to R2 likely occurring" | 2 | TBD | §4.6 (a) | Water Injection
W4 | High-WC producers loading PW system | "propose to reduce it to improve sector VRR" | 12 | TBD | §4.6 (c) | Water Injection

## Opportunities_Summary
All 8 De-Bottlenecking Opportunities — side by side
OPPORTUNITY COMPARISON
ID | Title | Category | 2026 low | 2026 high | 2026 mid | Full low | Full high | Conf. | Capex low ($M) | Capex high ($M)
4.5 | WI capacity uplift (SY-175 + SY-180 + cluster review) | Subsurface / WI | 2500 | 4000 | 3250 | 4000 | 5500 | Med-High | 2 | 28
4.7 | Surface back-pressure optimization | Surface | 1500 | 2500 | 2000 | 2300 | 3300 | Medium | 0.2 | 8
4.6 | Produced-water redistribution + R1↔R2 rebalancing | Subsurface / WI | 2000 | 2400 | 2200 | 2400 | 3200 | Medium | 0.5 | 1.5
4.1 | Stimulation roll-out beyond Obj 1.1C | Subsurface | 2500 | 2500 | 2500 | 5000 | 6000 | Medium | 8 | 12
4.3 | VSD / PWS retrofit campaign | Surface / Completion | 1600 | 1600 | 1600 | 3300 | 5500 | High | 2.4 | 4.8
4.4 | ESP upsize where pump at max frequency | Completion | 800 | 800 | 800 | 2800 | 2800 | Medium | 2 | 3.2
4.2 | BHFP rate-cap relaxation via skin reduction / PVT relocalization | Subsurface | 900 | 900 | 900 | 1800 | 1800 | Med-High | 0.2 | 0.5
4.8 | Inactive-string reactivation acceleration | Cross-cut Obj 1.1B | 1000 | 1000 | 1000 | 3920 | 3920 | High | 0.5 | 1

## Gain_Bridge
Production Gain Bridge — Current → 2026 Realistic Envelope
WATERFALL — STARTING POINT TO TARGET (BOPD)
Step | Item | Increment (BOPD) | Cumulative (BOPD)
Start | Current actual production | 0 | 75733
Step | §4.5 WI capacity uplift (SY-175 + SY-180 + cluster | 2500 | 78233
Step | §4.1 Stimulation roll-out beyond Obj 1.1 (×0.75 overlap) | 1875 | 80108
Step | §4.6 Produced-water redistribution + R1↔R2 rebalan | 2000 | 82108
Step | §4.7 Surface back-pressure optimization | 1500 | 83608
Step | §4.3 VSD / PWS retrofit campaign (×0.75 overlap) | 1200 | 84808
Step | §4.8 Inactive-string reactivation acceleration | 1000 | 85808
Step | §4.2 BHFP rate-cap relaxation via skin reduction / | 900 | 86708
Step | §4.4 ESP upsize where pump at max freque (×0.75 overlap) | 600 | 87308
End | 2026 realistic envelope | 0 | 87308

## Capex_vs_Gain
Capex vs Gain — Prioritization Matrix
BUBBLE DATA
ID | Title | Capex midpoint ($M) | 2026 gain midpoint (BOPD) | $/BOPD ratio | Confidence
4.5 | WI capacity uplift (SY-175 + SY-180 + cluster review) | 15 | 3250 | 4615 | Med-High
4.7 | Surface back-pressure optimization | 4.1 | 2000 | 2050 | Medium
4.6 | Produced-water redistribution + R1↔R2 rebalancing | 1 | 2200 | 455 | Medium
4.1 | Stimulation roll-out beyond Obj 1.1C | 10 | 2500 | 4000 | Medium
4.3 | VSD / PWS retrofit campaign | 3.6 | 1600 | 2250 | High
4.4 | ESP upsize where pump at max frequency | 2.6 | 800 | 3250 | Medium
4.2 | BHFP rate-cap relaxation via skin reduction / PVT relocalization | 0.35 | 900 | 389 | Med-High
4.8 | Inactive-string reactivation acceleration | 0.75 | 1000 | 750 | High

## Opp_4.5
§4.5 — WI capacity uplift (SY-175 + SY-180 + cluster review)
Category: Subsurface / WI · Confidence: Med-High
QUANTIFICATION
2026 realistic gain — low (BOPD) | 2500
2026 realistic gain — high (BOPD) | 4000
Full potential — low (BOPD) | 4000
Full potential — high (BOPD) | 5500
Capex bracket — low ($M) | 2
Capex bracket — high ($M) | 28
Capex midpoint per BOPD gained ($/BOPD) | 4615
Confidence | Med-High
MECHANISM
Phase 1: complete WO on SY-175 & SY-180 to recover 16,000 bwpd stranded capacity. Phase 2 (2027): Cluster #2 capacity uplift study based on Jan-2026 FCT. Phase 3: new WI well drilling if VRR confirms additional voidage to fill. Sector pressure recovery lifts Qo across ~30 R1/R2 producers. Saih Rawl analog (SPE 68222): ~12 % oil rate uplift per 30 % WI rate increase at mature waterflood stage.
PREREQUISITE DATA / WORK
Cluster #2 / SY-148 WS FCT (RM-mandated before SY-180 commissioning); G2V2 ML#5 forecast

## Opp_4.7
§4.7 — Surface back-pressure optimization
Category: Surface · Confidence: Medium
QUANTIFICATION
2026 realistic gain — low (BOPD) | 1500
2026 realistic gain — high (BOPD) | 2500
Full potential — low (BOPD) | 2300
Full potential — high (BOPD) | 3300
Capex bracket — low ($M) | 0.2
Capex bracket — high ($M) | 8
Capex midpoint per BOPD gained ($/BOPD) | 2050
Confidence | Medium
MECHANISM
Phase 1: Station header pressure setpoint review (CDS / RDS-1 / RDS-2). Each 10 psi separator pressure reduction across 80 R1 producers ≈ +800 BOPD. Phase 2: Selective flowline looping on 2-3 worst segments (>200 psi/km ΔP). Phase 3: Choke-on-test vs production-choke alignment.
PREREQUISITE DATA / WORK
January-2026 FCT report; GAP/Prosper IPM model; WHIP/WHFP-vs-time per well

## Opp_4.6
§4.6 — Produced-water redistribution + R1↔R2 rebalancing
Category: Subsurface / WI · Confidence: Medium
QUANTIFICATION
2026 realistic gain — low (BOPD) | 2000
2026 realistic gain — high (BOPD) | 2400
Full potential — low (BOPD) | 2400
Full potential — high (BOPD) | 3200
Capex bracket — low ($M) | 0.5
Capex bracket — high ($M) | 1.5
Capex midpoint per BOPD gained ($/BOPD) | 455
Confidence | Medium
MECHANISM
(a) Tracer + integrity diagnosis on 139-SS and 145-SS (RM flagged R1→R2 water loss). (b) Rebalance injection: redirect 3,000-5,000 bwpd from R2 to R1. (c) Selective shut-in / rate reduction on 6 worst high-WC producers (>85 % WC) to free PW capacity and improve sector VRR efficiency.
PREREQUISITE DATA / WORK
PW lab analysis (TDS, scaling, particulates, H₂S); injector PLT/CBL on 139-SS, 145-SS

## Opp_4.1
§4.1 — Stimulation roll-out beyond Obj 1.1C
Category: Subsurface · Confidence: Medium
QUANTIFICATION
2026 realistic gain — low (BOPD) | 2500
2026 realistic gain — high (BOPD) | 2500
Full potential — low (BOPD) | 5000
Full potential — high (BOPD) | 6000
Capex bracket — low ($M) | 8
Capex bracket — high ($M) | 12
Capex midpoint per BOPD gained ($/BOPD) | 4000
Confidence | Medium
MECHANISM
32+ R1 strings flagged 'Low intake / Low PIP / stim required' by RM. Obj 1.1C covers 5. Apply Naphtha+HCl recipe to 8-10 additional wells per year. Target wells with PI degradation D > 30 %/yr (1.1C methodology). Average gain +150 to +400 BOPD per well, declining 30 %/yr.
PREREQUISITE DATA / WORK
Per-well PI screening across 32 stim candidates (extension of 1.1C dashboard)

## Opp_4.3
§4.3 — VSD / PWS retrofit campaign
Category: Surface / Completion · Confidence: High
QUANTIFICATION
2026 realistic gain — low (BOPD) | 1600
2026 realistic gain — high (BOPD) | 1600
Full potential — low (BOPD) | 3300
Full potential — high (BOPD) | 5500
Capex bracket — low ($M) | 2.4
Capex bracket — high ($M) | 4.8
Capex midpoint per BOPD gained ($/BOPD) | 2250
Confidence | High
MECHANISM
22 strings flagged 'Low DP across choke / VSD required' — ESP-limited not reservoir-limited. Replace fixed-speed power with PWS-VSD; allows running at 55-60 Hz to push past choke-DP-limited operating point. Already proven on 10 Shah wells (SY-012, 019, 026, 035, 039, 097).
PREREQUISITE DATA / WORK
Power-system loading review (does Shah electrical infra support 8 more VSDs?)

## Opp_4.4
§4.4 — ESP upsize where pump at max frequency
Category: Completion · Confidence: Medium
QUANTIFICATION
2026 realistic gain — low (BOPD) | 800
2026 realistic gain — high (BOPD) | 800
Full potential — low (BOPD) | 2800
Full potential — high (BOPD) | 2800
Capex bracket — low ($M) | 2
Capex bracket — high ($M) | 3.2
Capex midpoint per BOPD gained ($/BOPD) | 3250
Confidence | Medium
MECHANISM
14 strings already at 55-60 Hz with no headroom (SY-073, 088, 094, 099, 100, 113). During next workover install pump from one tier higher in catalog (TE3300 → TE5000, GN3200 → GN4000). Combine with VSD where not already present.
PREREQUISITE DATA / WORK
Per-well ESP design review; align with existing WO schedule

## Opp_4.2
§4.2 — BHFP rate-cap relaxation via skin reduction / PVT relocalization
Category: Subsurface · Confidence: Med-High
QUANTIFICATION
2026 realistic gain — low (BOPD) | 900
2026 realistic gain — high (BOPD) | 900
Full potential — low (BOPD) | 1800
Full potential — high (BOPD) | 1800
Capex bracket — low ($M) | 0.2
Capex bracket — high ($M) | 0.5
Capex midpoint per BOPD gained ($/BOPD) | 389
Confidence | Med-High
MECHANISM
12 strings explicitly capped at low rate to keep BHFP ≥ Pb+100 (SY-040, 058, 064, 085, 120, 132, 135, 014). Two paths: (a) skin reduction via stimulation reduces drawdown for same Qo; (b) per-well revisit of Pb assumption — for some R1 wells, local Pb may be lower than 392 psi.
PREREQUISITE DATA / WORK
GAP/Prosper IPM model; PVT relocalization study

## Opp_4.8
§4.8 — Inactive-string reactivation acceleration
Category: Cross-cut Obj 1.1B · Confidence: High
QUANTIFICATION
2026 realistic gain — low (BOPD) | 1000
2026 realistic gain — high (BOPD) | 1000
Full potential — low (BOPD) | 3920
Full potential — high (BOPD) | 3920
Capex bracket — low ($M) | 0.5
Capex bracket — high ($M) | 1
Capex midpoint per BOPD gained ($/BOPD) | 750
Confidence | High
MECHANISM
14 inactive strings totaling 3,920 BOPD allowable (SY-035 PWS, SY-097 tie-in, SY-098 downsize, SY-115/117 ESP repl, SY-093 SAP-B fix). Speed of execution is the lever — every quarter of acceleration ≈ +1,000 BOPD avg uplift over the year.
PREREQUISITE DATA / WORK
Coordination with Obj 1.1B inactive-string KPI track

## Data_Gaps
Data Gaps — Required for Final Quantification
RANKED BY IMPACT-ON-DELIVERABLE
Rank | Item | Why needed
1 | January-2026 FCT report | Surface bottleneck quantification (§4.7) cannot move past estimate
2 | GAP/Prosper IPM surface model | Needed to run back-pressure sensitivities
3 | G2V2 reservoir model — ML#5 | Needed to quantify §4.5 oil response and §4.6 R1/R2 rebalancing
4 | Cluster #2 / SY-148 WS FCT | RM-mandated prerequisite for SY-180 commissioning (§4.5)
5 | PIDs / PFDs / vendor capacity sheets | CDS, RDS-1, RDS-2, WI clusters
6 | Produced water lab analysis | TDS, scaling, particulates, H₂S — needed for §4.6 design
7 | WHIP-vs-time and WHPP-vs-time per well | Needed to validate flowline-restriction hypothesis (§4.7)
8 | Injector PLT / CBL logs (139-SS, 145-SS) | Needed for §4.6 (a) integrity hypothesis
9 | Per-well PI screening across 32 stim candidates | Extension of 1.1C methodology to scope §4.1

## Field_Totals
Field-Level Totals from Q2-2026 Allowable file
OIL — TOTAL AT SHAH
| Allowable | FTR (incl. inactive) | FAR
Total at SHAH | 76671 | 79983 | 75733
Total at JD | 69016 | 73482 | 68172
Including Inactive — Allowable | 80591 | 79983 | —
WATER INJECTION — TOTAL AT SHAH (bwpd)
Cluster | Allowable w/ SY-175&180 | Max w/o | Tech rate | Actual | Notes
Cluster #1 | 26000 | 26000 | 42200 | 34000 | WI-C R1
Cluster #2 | 24600 | 19000 | 28800 | 19000 | WI-C+CN R1
WI to R2 | 25500 | 27000 | 34500 | 27000
WI-C only R1 | 16100 | 18000 | 20500 | 18000
WI-R1 C+CN | 25100 | 18000 | — | — | Awaiting SY-175/180
Total | 50600 | 45000 | 71000 | 53000 | Field-level

## Workshop_Agenda
Q3-2026 Technical Workshop Agenda
Per KoM plan — bi-weekly progress meetings + Q3 Technical WS
AGENDA ITEMS
1. | Validate the bottleneck classification (9 categories) against AON's own internal view
2. | Confirm the FCT findings (once delivered) and align on §4.7 Surface back-pressure priorities
3. | Decide on §4.6 tracer campaign scope — which WI/producer pairs (139-SS, 145-SS first)
4. | Approve the §4.3 VSD retrofit shortlist and 2026 execution sequence
5. | Align on §4.5 Phase 2 Cluster #2 uplift study scope and timing
6. | Cross-reference §4.1 stim backlog with Obj 1.1C selected 5 to avoid double-counting
7. | Workshop output: signed-off opportunity list with executive owners assigned per item