## Slide 1
PC26 · Objective 1.1D
Shah Field De-Bottlenecking
Surface & subsurface opportunities · quantified catalogue · 2026 envelope
TotalEnergies ALSG × ADNOC Onshore Asset Lead FP: Andrey Semenov Issued 19-May-2026
75,733
BOPD field actual
+10–12k
BOPD 2026 envelope
8
opportunities
9
data gaps blocking final

## Slide 2
Executive Summary
PC26 · Obj 1.1D
PC26 · Obj 1.1D · Shah De-Bottlenecking · TotalEnergies ALSG × ADNOC Onshore
2 / 12
BOPD CURRENT FAR
75,733
Q1-2026 · vs 79,983 TR (–5.6%)
BOPD 2026 UPLIFT
+10–12k
+13% field oil within 12 months
OPPORTUNITIES CATALOGUED
8
5 subsurface · 2 surface · 1 cross
CRITICAL DATA GAPS
9
FCT + IPM model top of list
KEY FINDINGS
Sub-surface levers dominate
Of 124 active strings, 36 are stim candidates (S1) and 55 are >60% WC (S2).
Reservoir VRR is the upstream control variable — restoring SY-175 + SY-180 unlocks +16,000 bwpd of stranded injection.
Saih Rawl analog (SPE 68222): +12% oil per +30% WI at mature waterflood.
Surface side under-quantified — pending FCT
§4.7 back-pressure estimate (+1.5–2.5 kBOPD) carries widest uncertainty.
Each 10 psi separator-pressure cut ≈ +800 BOPD across 80 R1 producers.
GAP/Prosper IPM model + Jan-2026 FCT report are blocking inputs.
Execution path: front-load WI uplift + VSD retrofits
Top 3 by 2026 gain: §4.5 WI capacity, §4.7 back-pressure, §4.6 PW redistribution.
VSD/PWS retrofit (§4.3) is highest-confidence — proven on 10 wells already.
After 25% overlap deduction, realistic 2026 envelope ~10,000–12,000 BOPD.

## Slide 3
Field baseline — Allowable, TR, Actual
§ Baseline
PC26 · Obj 1.1D · Shah De-Bottlenecking · TotalEnergies ALSG × ADNOC Onshore
3 / 12
OIL PRODUCTION (BOPD)
Chart: 
| Actual (FAR) | Allowable | TR | Allow w/ Inactive | Deliv. ceiling
BOPD | 75733 | 76671 | 79983 | 80591 | 102752
WATER INJECTION (bwpd)
Scenario | Cluster #1 | Cluster #2 | Total target | Actual
w/ SY-175 + SY-180 | 26,000 | 24,600 | 50,600 | —
w/o SY-175 + SY-180 | 26,000 | 19,000 | 45,000 | 53,000
Technical rate | 42,200 | 28,800 | 71,000 | —
Cluster physical cap | 26,000 | 25,000 | — | —
Gap analysis: 4,250 BOPD under-TR (5.6%). WI under-injecting by ~18,000 bwpd vs technical — SY-175/180 alone recovers ~16,000.
Source: Q2-2026 Allowable file, sheet Q2-2026 OP Allowable RM_Upd (rows 11–134) and Q2-2026 WI Allowable. Inactive strings booked at 3,920 BOPD.
Gap vs TR
4,250 BOPD
Under-WI
18,000 bwpd
Wells classed
124 active
Inactive booked
3,920 BOPD

## Slide 4
Bottleneck map — 9 root causes from RM comments
§ Classification
PC26 · Obj 1.1D · Shah De-Bottlenecking · TotalEnergies ALSG × ADNOC Onshore
4 / 12
ID | Category | Group | Wells | BOPD lost | Opp.
S1 | Low PIP / stim candidate | Subsurface | 36 | ~12,000 | §4.1
S2 | High WC (>60%) | Subsurface | 55 | ~7,000 | §4.6 + 1.2A
S3 | Low BHFP / close to Pb | Subsurface | 10 | ~1,800 | §4.2
S4 | Inactive — WO backlog | Subsurface | 9 | ~3,920 | §4.8 + 1.1B
S5 | Reservoir P depletion | Subsurface | 1 | ~5,000 | §4.5
C1 | Low ΔP choke / VSD req. | Surface/Completion | 17 | ~6,500 | §4.3
C2 | ESP at max frequency | Completion | 13 | ~3,500 | §4.4
C3 | Surface back-pressure (proxy) | Surface | 12 | TBD | §4.7
W1 | Cluster cap 25/26 Mbwpd | Water Injection | — | — | §4.5 Ph2
W2 | WI integrity (SY-175, SY-180) | Water Injection | 2 | 16k bwpd | §4.5 Ph1
W3 | R1↔R2 inter-reservoir loss | Water Injection | 2 | — | §4.6 (a)
W4 | High-WC producers loading PW | Water Injection | 13 | — | §4.6 (c)
Wells per category
Chart: 
| S1 | S2 | S3 | S4 | S5 | C1 | C2 | C3 | W1 | W2 | W3 | W4
wells | 36 | 55 | 10 | 9 | 1 | 17 | 13 | 12 | 0 | 2 | 2 | 13
8 producer-side categories + 4 WI-side categories. Strings can fall into multiple categories — counts are not mutually exclusive.
Highest-leverage category: S1 (stim candidates) at 36 wells × ~12,000 BOPD lost vs SH cap; addressed by §4.1 (Obj 1.1C extension) + selective §4.2 work. Surface category C3 (back-pressure proxy) is unquantified pending the Jan-2026 FCT report — represents the largest analytical uncertainty.

## Slide 5
Bottleneck stack — wells & BOPD lost by category
§ Quantification
PC26 · Obj 1.1D · Shah De-Bottlenecking · TotalEnergies ALSG × ADNOC Onshore
5 / 12
Where the 4,250 BOPD TR-gap (+ further upside) comes from
Chart: 
| S1 stim | S2 high WC | S3 low BHFP | S4 inactive | S5 depletion | C1 VSD req | C2 ESP max | C3 back-pres.
BOPD lost vs SH cap | 12000 | 7000 | 1800 | 3920 | 5000 | 6500 | 3500 | 3000
* C3 surface back-pressure is a midpoint proxy (2,000-4,000 BOPD), pending FCT
CATEGORY → OPPORTUNITY MAP
S1 + S3
→ §4.1 stim + §4.2 BHFP
S2 + W4
→ §4.6 PW redistribution
S4
→ §4.8 reactivation accel.
S5 + W1-3
→ §4.5 WI capacity uplift
C1
→ §4.3 VSD/PWS retrofit
C2
→ §4.4 ESP upsize
C3
→ §4.7 back-pressure (FCT)
Each Allowable RM-comment row maps to ≥1 category. 124 strings → ~210 category hits → 8 quantified opportunities.

## Slide 6
§4.5 — WI capacity uplift (SY-175 + SY-180 + cluster review)
Deep-dive 1/4
PC26 · Obj 1.1D · Shah De-Bottlenecking · TotalEnergies ALSG × ADNOC Onshore
6 / 12
Subsurface / Water Injection · Confidence: Med-High
2026 REALISTIC GAIN
+2,500–4,000 BOPD
FULL POTENTIAL
+4,000–5,500 BOPD
CAPEX BRACKET
$2–28M
MECHANISM
Phase 1 (Q2/Q3-2026): complete the WO on SY-175 + SY-180 to recover 16,000 bwpd of stranded injection capacity. RM warns to run an FCT in Cluster #2 / SY-148 WS before SY-180 commissioning (current 19,000 bwpd vs 28,800 bwpd technical).
Phase 2 (2027): Cluster #2 capacity uplift study if FCT confirms 26 Mbwpd ceiling — evaluate manifold/pump capacity addition to 35 Mbwpd.
Phase 3: new WI well drilling if reservoir VRR analysis confirms incremental voidage to fill. Saih Rawl analog (SPE 68222): +12% oil rate per +30% WI rate at mature waterflood.
PREREQUISITE DATA / WORK
Cluster #2 / SY-148 WS FCT (RM-mandated before SY-180 commissioning) · G2V2 ML#5 reservoir forecast · sector VRR breakdown
RECOMMENDATION · Front-load Phase 1 in Q2/Q3-2026 — single largest 2026 gain ($2-3M capex, +2,500-4,000 BOPD). Phase 2 conditional on FCT outcome.

## Slide 7
§4.7 — Surface back-pressure optimization
Deep-dive 2/4
PC26 · Obj 1.1D · Shah De-Bottlenecking · TotalEnergies ALSG × ADNOC Onshore
7 / 12
Surface · KoM focus area · Confidence: Medium
2026 REALISTIC GAIN
+1,500–2,500 BOPD
FULL POTENTIAL
+2,300–3,300 BOPD
CAPEX BRACKET
$0.2–8M
MECHANISM
KoM explicit ask — proxy indicators from Allowable: wells at full choke, ESP at 50 Hz with rate plateauing (downstream restriction); WHFT 150-162°F (high flowline pressure); non-uniform separator pressure.
Phase 1: station header setpoint review (CDS / RDS-1 / RDS-2). Each 10 psi separator cut ≈ +800 BOPD across 80 R1 producers.
Phase 2: flowline looping on 2-3 worst segments (>200 psi/km ΔP).
Phase 3: choke-on-test vs production-choke bias alignment.
PREREQUISITE DATA / WORK
January-2026 FCT report (BLOCKING) · GAP/Prosper IPM surface model · WHIP/WHFP-vs-time per well · CDS/RDS PFD & PIDs
RECOMMENDATION · Phase 1 ($0.2M control changes) achievable in <90 days once FCT lands. Surface CapEx slate for Phase 2 to be scoped after Q3-2026 WS.

## Slide 8
§4.6 — Produced-water redistribution + R1↔R2 rebalancing
Deep-dive 3/4
PC26 · Obj 1.1D · Shah De-Bottlenecking · TotalEnergies ALSG × ADNOC Onshore
8 / 12
Subsurface / WI · Confidence: Medium
2026 REALISTIC GAIN
+2,000–2,400 BOPD
FULL POTENTIAL
+2,400–3,200 BOPD
CAPEX BRACKET
$0.5–1.5M
MECHANISM
(a) Tracer + integrity diagnosis on 139-SS & 145-SS — RM flagged "Water loss to R2 likely occurring due to communication between reservoir units". Confirm with chemical tracers, remediate with cement squeeze if zonal isolation lost.
(b) Rebalance 3,000-5,000 bwpd from R2 → R1 (R2 receives 27,000 vs 34,500 target; R1-C only at 18,000 vs 20,500 target).
(c) Selective shut-in / rate reduction on 6 worst >85% WC producers — frees ~20,000 bwpd PW capacity, improves sector VRR.
PREREQUISITE DATA / WORK
PW lab analysis (TDS, scaling, particulates, H₂S) · injector PLT/CBL on 139-SS and 145-SS · G2V2 rerun with re-balanced injection
RECOMMENDATION · Low-cost / high-leverage. Sequence tracer campaign Q3-2026 — integrity findings drive cement-squeeze scope.

## Slide 9
§4.1 — Stimulation roll-out beyond Obj 1.1C
Deep-dive 4/4
PC26 · Obj 1.1D · Shah De-Bottlenecking · TotalEnergies ALSG × ADNOC Onshore
9 / 12
Subsurface · Confidence: Medium
2026 REALISTIC GAIN
+2,500 BOPD
FULL POTENTIAL
+5,000–6,000 BOPD
CAPEX BRACKET
$8–12M
MECHANISM
32+ R1 strings flagged "Low intake / Low PIP / stim required" by RM. Obj 1.1C scopes only 5. Apply proven Naphtha + HCl recipe to 8-10 additional R1 wells per year as a sustained program.
Target wells with PI degradation D > 30%/yr (extend the 1.1C dashboard methodology). Average gain +150-400 BOPD per well, 30%/yr decline post-job. Backlog of 25 candidates × 250 BOPD avg ≈ +6,000 BOPD at peak.
PREREQUISITE DATA / WORK
Per-well PI screening across 32 stim candidates (1.1C dashboard extension) · workover-rig availability schedule
RECOMMENDATION · Commission 10-well stim program for Q3-2026 → Q4-2027. Coordinate with Obj 1.1C to avoid double-counting the 5 wells already in plan.

## Slide 10
Consolidated ranking & gain bridge
§ Roadmap
PC26 · Obj 1.1D · Shah De-Bottlenecking · TotalEnergies ALSG × ADNOC Onshore
10 / 12
# | Opportunity | 2026 realistic | Full pot. | Conf | Capex
1 | §4.5 WI capacity (SY-175/180 + cluster) | +2,500–4,000 | +4,000–5,500 | M-H | $$
2 | §4.7 Surface back-pressure | +1,500–2,500 | +2,300–3,300 | M | $ → $$$
3 | §4.6 PW redistribution + R1/R2 | +2,000 | +2,400–3,200 | M | $
4 | §4.1 Stim roll-out beyond 1.1C | +2,500 | +5,000–6,000 | M | $$$
5 | §4.3 VSD/PWS retrofit | +1,600 | +3,300–5,500 | H | $$
6 | §4.4 ESP upsize (piggyback WO) | +800 | +2,800 | M | $$
7 | §4.2 BHFP cap relaxation | +900 | +1,800 | M-H | low
8 | §4.8 Inactive-string reactivation | +1,000 | booked in TR | H | low
GAIN BRIDGE — current → 2026 envelope
Chart: 
| Start | §4.5 | §4.7 | §4.6 | §4.1 | §4.3 | §4.4 | §4.2 | §4.8 | Envelope
Cumulative BOPD | 75733 | 78233 | 79733 | 81733 | 83608 | 84808 | 85408 | 86308 | 87308 | 87308
2026 realistic envelope (after 25% overlap deduction on §4.1+§4.3+§4.4): 11,575 BOPD uplift → 87,308 BOPD total (+15%)
Comparable to Saih Rawl Shuaiba debottlenecking (SPE 68222 analog): +6,300 BOPD on a smaller system via choke automation + WI redistribution.

## Slide 11
Data gaps & next steps
§ Roadmap
PC26 · Obj 1.1D · Shah De-Bottlenecking · TotalEnergies ALSG × ADNOC Onshore
11 / 12
9 CRITICAL DATA ITEMS REQUIRED
# | Item | Why
1 | January-2026 FCT report | Blocking §4.7
2 | GAP/Prosper IPM surface model | Blocking §4.7 & §4.2
3 | G2V2 reservoir model — ML#5 | Blocking §4.5 & §4.6 oil response
4 | Cluster #2 / SY-148 WS FCT | Blocking SY-180 commissioning
5 | PIDs / PFDs / vendor capacity | CDS, RDS-1, RDS-2, WI clusters
6 | Produced water lab analysis | TDS, scaling, particulates, H₂S
7 | WHIP/WHFP-vs-time per well | §4.7 validation
8 | Injector PLT/CBL (139-SS, 145-SS) | §4.6 (a) integrity hypothesis
9 | Per-well PI screening (32 cands.) | §4.1 scoping
TIMELINE — NEXT 90 DAYS
Now
Pull FCT
+ PIDs
+30 d
Per-well PI
screen (§4.1)
+60 d
GAP/Prosper
rerun
+90 d
Q3 Technical
Workshop
Q3-2026 Technical WS — agenda highlights
Validate the 9-category bottleneck map vs AON internal view
Approve §4.3 VSD retrofit shortlist & 2026 execution sequence
Confirm FCT findings; align on §4.7 surface back-pressure priorities
Decide §4.6 tracer campaign scope (139-SS, 145-SS first)
Cross-reference §4.1 stim backlog with Obj 1.1C selected 5
Sign off opportunity list with executive owners per item
Items #1–4 are blockers for tightening the §4.5 and §4.7 estimates — the two largest 2026 opportunities.

## Slide 12
Conclusions
PC26 · Obj 1.1D · Shah De-Bottlenecking
1
Field is under-delivering TR by 4,250 BOPD (5.6%) — bottleneck spread across subsurface (60%) and surface/WI (40%).
2
2026 realistic uplift envelope is +10,000–12,000 BOPD (+13%), comparable to Saih Rawl Shuaiba (SPE 68222) outcome.
3
Largest single 2026 lever is §4.5 WI capacity uplift (SY-175/180 + Cluster #2): +2,500–4,000 BOPD at $2–3M Phase 1 capex.
4
Highest-confidence quick win is §4.3 VSD/PWS retrofit: +1,600 BOPD at $2.4–4.8M, mechanism proven on 10 Shah wells.
5
Final quantification blocked by 4 data items — Jan-2026 FCT report is the single most important data request.
Next checkpoint: Q3-2026 Technical Workshop — opportunity sign-off + owner assignment